## Sheet1
This template is brought to you by actiTIME, a smart time tracking tool. Visit our website to sign up for a free 30-day trial or get free business resources:
https://www.actitime.com/
If you want to use this template for your project, open the "File" settings and click on "Make a copy."
eCOMMERCE PROJECT PLAN TEMPLATE
Project name: Online store launch
Project manager: J. J. Grimes
Project start and end dates: November 1 - April 1
Goals | 1. Launch an online store by January 1
2. Launch a SoMe marketing campaign
3. Increase website traffic by 100.000 visits a month (deadline: March 1)
Deliverables | 1. Fully functional eCommerce website
2. Comprehensive marketing strategy
3. Google Analytics setup
Budget | Project management stages / milestones |  |  | Staff-related costs |  |  |  | Marketing costs |  | Miscellaneous costs |  | Total costs
| 1. Planning |  |  | $5.000 |  |  |  | 0 |  | $500 |  | $5.500
| 2. Execution |  |  | $15.000 |  |  |  | $10.000 |  | $500 |  | $25.500
3. Monitoring
4. Analysis
TIMELINE
Milestones | Task | Employee | Estimate | Start date | End date | Status | January | February | March | April | May |  | June | July
Planning | Market researh | J.J. Grimes | 20 hours | 2021-01-02 | 2021-01-06 | Completed
| Cost estimation | P. Peterson | 15 hours | 2021-01-02 | 2021-01-07 | In progress
| Marketing plan | E. Rudzenko | 20 hours | 2021-01-02 | 2021-01-08 | To-do
| Scheduling | J.J. Grimes | 8 hours | 2021-01-08 | 2021-01-10 | To-do
| Plan finalization | J.J. Grimes | 5 hours | 2021-01-10 | 2021-01-11 | To-do
| Plan approval | J.J. Grimes | 3 hours | 2021-01-16 | 2021-01-16 | To-do
Execution | Task 1
Task 2
Task 3
Task 4
Task 5
Task 1
Taks 2
Task 3
Task 4
Task 5
Task 1
Task 2
Task 3
Task 4
Task 5
Monitoring | Task 1
Task 2
Task 3
Task 4
Task 5
Analysis | Task 1
Task 2
Task 3
Task 4
Task 5
Key performance indicators | 1.
2.
3.
4.
5.
6.
7.
8.
9.
10.
Marketing plan | Key deliverables | Tasks |  | Deadline | Employee
| 1. eMail marketing campaign | Lead analysis |  | January 5 | J.J. Grimes
|  | Visual design |  | January 10
|  | Content creation |  | January 10
|  | eMail automation |  | January 10
|  | Analytics |  | March 20
2.
3.